## Sheet5 (hidden)
TRANSFORM HEALTH COMMENTS
TRANSFORM HEALTH NATIONAL COORDINATING PARTNER-KENYA
| PROPOSAL BUDGET FOR 6 MONTHS | No. | Unit Cost | Frequency | Unit of Frequency | Total (Kshs) | Total (USD)
Activity 1. Establish the national coalition platform with initial 20 member organization
1.1: | Conduct a meeting of the national project steering committee to disseminate the findings of the initial landscape analysis and discuss roll out of expanded research on digital health
| Full day conference package @ 4,000 * 20 pax | 20 | 4000 | 1 |  | 80000 | 800
| Honorarium for facilitator @ Ksh 10,000 | 1 | 10000 | 1 |  | 10000 | 100
| Rapportuer @ 10,000/= per day | 1 | 10000 | 1 |  | 10000 | 100
| Transport reimbursement for participants - 17 pax @ 2,000 | 17 | 2000 | 1 |  | 34000 | 340
| Meeting material (mobilization, printing, photocopying, PPEs etc) | 1 | 20000 | 1 |  | 20000 | 200
| Coordination transport for staff | 1 | 7000 | 1 |  | 7000 | 70
| Subtotal |  |  |  |  | 161000 | 1610
1.2: | Undertake indepth research on equitable access to digital health technologies and universal health coverage in Kenya
1.2.1 | Develop Terms of Reference and recruit consultant for the research
| Engage consultant in conducting research | 1 | 30000 | 33 | days? | 990000 | 9900 | what is the 33 unit number of days? - This is the estimated number of days the consult
| Subtotal |  |  |  |  | 990000 | 9900
1.2.2 | Facilitate the consultant to conduct focus group discussions and data collection from both urban, peri urban and rural counties
Logistics
| Accommodation and meals for consultants and staff | 5 | 12000 | 12 | days? | 720000 | 7200
| Material cost & mobilization | 1 | 30000 | 6 |  | 180000 | 1800
| Hall hire for FGD | 1 | 10000 | 6 |  | 60000 | 600
| Refreshments | 25 | 500 | 6 |  | 75000 | 750
| Transport reimbursements | 25 | 1000 | 6 |  | 150000 | 1500
| Return air travel for 5 pax | 5 | 20000 | 4 |  | 400000 | 4000 | Where will people be flying to - please state locations and share links for costs
| Coordination transport and transfers | 1 | 30000 | 6 |  | 180000 | 1800
Virtual FGD
| Data reimbursements for participants | 25 | 1000 | 6 |  | 150000 | 1500 | Please add in what the purpose of data reimbursments are
| Sub-total |  |  |  |  | 1915000 | 19150
1.2.3 | Conduct a meeting of the national project steering committee to validate the findings of the research
| Data reimbursements | 25 | 2000 | 1 |  | 50000 | 500 | Please add in what the purpose of data reimbursments are
| Mobilization costs | 1 | 5000 | 1 |  | 5000 | 50 | Please add what these moblisation costs pay for?
| Subtotal |  |  |  |  | 55000 | 550
1.3 | Launch National Campaign during Digital Health Week
1.3.1 | Conduct Social Media validation of the issues documented from the research findings
| Staff time | 1 | 0 | 0 |  | 0 | 0
| Sub total |  |  |  |  | 0 | 0
1.3.2 | Disseminate the findings of the research on mainstream media (TV / radio talk shows )
| Main media | 1 | 500000 | 1 |  | 500000 | 5000 | What will this pay for please add in detials in column B
| Sub total |  |  |  |  | 500000 | 5000
1.3.3 | Conduct a national conference with various actors in the digital health and UHC space in Kenya to disseminate the findings of the research and to officially launch the Transform Health Coalition in Kenya
| Accommodation and meals for participants from out of town | 10 | 12000 | 2 |  | 240000 | 2400
| Conference package for 35 pax @ 4,000 pp for one day | 35 | 4000 | 1 |  | 140000 | 1400
| Honorarium for facilitator @ Ksh 10,000 | 3 | 10000 | 1 |  | 30000 | 300
| Rapportuer Fee @ 20,000/= per day | 1 | 20000 | 1 |  | 20000 | 200
| Transport reimbursement for participants in Nairobi county | 25 | 2000 | 1 |  | 50000 | 500
| Transport reimbursement for participants out of Nairobi county | 5 | 5000 | 1 |  | 25000 | 250
| Air transport for 5 participants | 5 | 20000 | 1 |  | 100000 | 1000
| Transfers and coordination | 1 | 25000 | 1 |  | 25000 | 250
| Design of banners/report | 1 | 20000 | 5 |  | 100000 | 1000
| Meeting material (mobilization, PPEs etc) | 1 | 25000 | 1 |  | 25000 | 250
| Printing of materials for launch | 200 | 900 | 1 |  | 180000 | 1800
| Sub total |  |  |  |  | 935000 | 9350
1.4 | Establish the Transform Health National Coalition
1.4.1 | Invite 20 members to join the Transform Health Coalition
| Staff time | 1 | 0 | 0 |  | 0 | 0
| Sub total |  |  |  |  | 0 | 0
[6 empty] | 0 | 0
1.4.2. | Conduct a two-day introductory meeting and training to introduce Transform Health; develop a Memorandum of Understanding; and develop a shared understanding of UHC in the digital age |  |  |  |  | 0 | 0 | 1.4.2 and 1.5 should be collapsed into a single event 4 days
| Conference costs for 25 pax @ 4,000 pp for 1 day | 25 | 4000 | 2 |  | 200000 | 2000
| Material costs (printing, photocopying, mobilization, PPEs etc) | 1 | 40000 | 1 |  | 40000 | 400
| Transport reimbursements to participants | 20 | 2000 | 1 |  | 40000 | 400
| Honorarium | 3 | 10000 | 2 |  | 60000 | 600
| Coordination transport for staff | 1 | 7000 | 2 |  | 14000 | 140
| Facilitation honorarium | 3 | 10000 | 2 |  | 60000 | 600
| Rapporteur | 1 | 50000 | 1 |  | 50000 | 500
[6 empty] | 0 | 0
[6 empty] | 464000 | 4640
1.5 | Conduct a two -day workshop of Coalition partners to brainstorm and develop the a work plan, Theory of Change and national campaign and influencing strategy for the National Coalition
| Conference costs for 25 pax @ 4,000 pp for 1 day | 25 | 4000 | 2 |  | 200000 | 2000
| Accomodation and meals for 25 pax | 25 | 12000 | 3 |  | 900000 | 9000
| Material costs (printing, photocopying, mobilization, PPEs etc) | 1 | 30000 | 1 |  | 30000 | 300
| Transport reimbursements to participants | 17 | 2000 | 2 |  | 68000 | 680
| Coordination transport for staff | 1 | 7000 | 2 |  | 14000 | 140
| Facilitation honorarium | 3 | 10000 | 2 |  | 60000 | 600
| Rapporteur | 1 | 50000 | 1 |  | 50000 | 500
[6 empty] | 0 | 0
[6 empty] | 1322000 | 13220
1.5.1 | Develop Terms of Reference and recruit consultant for the Theory of Change
| Engage a consultant | 1 | 30000 | 9 |  | 270000 | 2700 | This should be conducted in house. Transform Health can facilitate
| Sub total |  |  |  |  | 270000 | 2700
1.5.2 | Conduct a meeting of the national steering committee to validate the Theory of Change
| Data reimbursements | 25 | 2000 | 1 |  | 50000 | 500 | Please add in what the purpose of data reimbursments are
| Mobilization | 1 | 5000 | 1 |  | 5000 | 50 | Please add what these moblisation costs pay for?
| Subtotal |  |  |  |  | 55000 | 550
1.5.3. | Develop Terms of Reference for a consultant for work plan development and for communications & campaign strategy
| Engage a consultant | 1 | 30000 | 9 |  | 270000 | 2700 | This should be conducted in house. Transform Health can facilitate
| Sub total |  |  |  |  | 270000 | 2700
1.5.4. | Conduct meeeting of the national steering committee to validate the work plan and campaign strategy
| Data reimbursements | 25 | 2000 | 1 |  | 50000 | 500 | Please add in what the purpose of data reimbursments are?
| Mobilization | 1 | 5000 | 1 |  | 5000 | 50 | What cost is this in relation to mobilisation - state details in column B?
| Subtotal |  |  |  |  | 55000 | 550
| Project Activities Total |  |  |  |  | 6992000 | 69920
Contribution To Project Staff Salaries
| Program Manager Health & Governance % of staff time per month | 1 | 128000 | 3 | months | 384000 | 3840 | What is the actual % please state in column B for each staff member
| Program Officer Health & Governance % of staff time per month | 1 | 120000 | 3 | months | 360000 | 3600 | What is the actual % please state in column B for each staff member
| DED % of staff time per month | 1 | 80000 | 3 | months | 240000 | 2400 | What is the actual % please state in column B for each staff member
| Executive Director % of staff time per month | 1 | 50000 | 3 | months | 150000 | 1500 | What is the actual % please state in column B for each staff member
| M & E advisor % of staff time per month | 1 | 75000 | 3 | months | 225000 | 2250 | What is the actual % please state in column B for each staff member
| Finance & Administration Manager % of staff time per month | 1 | 90000 | 3 | months | 270000 | 2700 | What is the actual % please state in column B for each staff member
| Communications Officer % of staff time per month | 1 | 75000 | 3 | months | 225000 | 2250 | What is the actual % please state in column B for each staff member
| Sub total |  |  |  |  | 1854000 | 18540 | Staff and Overhead costs are 30% of total costs - by donor standards this is too high - should be around 15 to 20%
General Office Administration Costs
| Utilities, Internet Costs @ 250,000 per month | 1 | 341666.67 | 3 |  | 1025000.01 | 10250.0001
| Sub total |  |  |  |  | 1025000.01 | 10250.0001
| Total budget |  |  |  |  | 9871000.01 | 98710.0001
Note on B16: ====== ID#AAAAPhasqtE Frank Smith (2021-09-28 09:58:19) This should be covered in the landscape analysis and may not be necessary during this phase. Consider including this in the next plan
Note on B53: ====== ID#AAAAPhasqtI Frank Smith (2021-09-28 10:00:03) Here is where we want to launch the landscape analysis as a report with strong recommendations.

## TAB 2 Budget (hidden)
TRANSFORM HEALTH COMMENTS
TRANSFORM HEALTH NATIONAL COORDINATING PARTNER-KENYA
| PROPOSAL BUDGET FOR 6 MONTHS | No. | Unit Cost | Frequency | Total (Kshs) | Total (USD)
Activity 1. Establish the national coalition platform with initial 20 member organization
1.1: | Conduct a meeting of the national project steering committee to disseminate the findings of the initial landscape analysis and discuss roll out of expanded research on digital health
| Full day conference package @ 4,000 * 20 pax | 20 | 4000 | 1 | 80000 | 800
| Honorarium for facilitator @ Ksh 10,000 | 1 | 10000 | 1 | 10000 | 100
| Rapportuer @ 10,000/= per day | 1 | 10000 | 1 | 10000 | 100
| Transport reimbursement for participants - 17 pax @ 2,000 | 17 | 2000 | 1 | 34000 | 340
| Meeting material (mobilization, printing, photocopying, PPEs etc) | 1 | 20000 | 1 | 20000 | 200
| Coordination transport for staff | 1 | 7000 | 1 | 7000 | 70
| Subtotal |  |  |  | 161000 | 1610
1.2: | Undertake indepth research on equitable access to digital health technologies and universal health coverage in Kenya
1.2.1 | Develop Terms of Reference and recruit consultant for the research
| Engage consultant in conducting research | 1 | 30000 | 33 | 990000 | 9900
| Subtotal |  |  |  | 990000 | 9900
1.2.2 | Facilitate the consultant to conduct focus group discussions and data collection from both urban, peri urban and rural counties
Logistics
| Accommodation and meals for consultants and staff | 5 | 12000 | 12 | 720000 | 7200
| Material cost & mobilization | 1 | 30000 | 6 | 180000 | 1800
| Hall hire for FGD | 1 | 10000 | 6 | 60000 | 600
| Refreshments | 25 | 500 | 6 | 75000 | 750
| Transport reimbursements | 25 | 1000 | 6 | 150000 | 1500
| Return air travel for 5 pax | 5 | 20000 | 4 | 400000 | 4000
| Coordination transport and transfers | 1 | 30000 | 6 | 180000 | 1800
Virtual FGD
| Data reimbursements for participants | 25 | 1000 | 6 | 150000 | 1500
| Sub-total |  |  |  | 1915000 | 19150
1.2.3 | Conduct a meeting of the national project steering committee to validate the findings of the research
| Data reimbursements | 25 | 2000 | 1 | 50000 | 500
| Mobilization costs | 1 | 5000 | 1 | 5000 | 50
| Subtotal |  |  |  | 55000 | 550
1.3 | Launch National Campaign during Digital Health Week
1.3.1 | Conduct Social Media validation of the issues documented from the research findings
| Staff time | 1 | 0 | 0 | 0 | 0
| Sub total |  |  |  | 0 | 0
1.3.2 | Disseminate the findings of the research on mainstream media (TV / radio talk shows )
| Main media | 1 | 500000 | 1 | 500000 | 5000
| Sub total |  |  |  | 500000 | 5000
1.3.3 | Conduct a national conference with various actors in the digital health and UHC space in Kenya to disseminate the findings of the research and to officially launch the Transform Health Coalition in Kenya
| Accommodation and meals for participants from out of town | 10 | 12000 | 2 | 240000 | 2400
| Conference package for 35 pax @ 4,000 pp for one day | 35 | 4000 | 1 | 140000 | 1400
| Honorarium for facilitator @ Ksh 10,000 | 3 | 10000 | 1 | 30000 | 300
| Rapportuer Fee @ 20,000/= per day | 1 | 20000 | 1 | 20000 | 200
| Transport reimbursement for participants in Nairobi county | 25 | 2000 | 1 | 50000 | 500
| Transport reimbursement for participants out of Nairobi county | 5 | 5000 | 1 | 25000 | 250
| Air transport for 5 participants | 5 | 20000 | 1 | 100000 | 1000
| Transfers and coordination | 1 | 25000 | 1 | 25000 | 250
| Design of banners/report | 1 | 20000 | 5 | 100000 | 1000
| Meeting material (mobilization, PPEs etc) | 1 | 25000 | 1 | 25000 | 250
| Printing of materials for launch | 200 | 900 | 1 | 180000 | 1800
| Sub total |  |  |  | 935000 | 9350
1.4 | Establish the Transform Health National Coalition
1.4.1 | Invite 20 members to join the Transform Health Coalition
| Staff time | 1 | 0 | 0 | 0 | 0
| Sub total |  |  |  | 0 | 0
[5 empty] | 0 | 0
1.4.2. | Conduct a two-day introductory meeting and training to introduce Transform Health; develop a Memorandum of Understanding; and develop a shared understanding of UHC in the digital age |  |  |  | 0 | 0
| Conference costs for 25 pax @ 4,000 pp for 1 day | 25 | 4000 | 2 | 200000 | 2000
| Material costs (printing, photocopying, mobilization, PPEs etc) | 1 | 40000 | 1 | 40000 | 400
| Transport reimbursements to participants | 20 | 2000 | 1 | 40000 | 400
| Honorarium | 3 | 10000 | 2 | 60000 | 600
| Coordination transport for staff | 1 | 7000 | 2 | 14000 | 140
| Facilitation honorarium | 3 | 10000 | 2 | 60000 | 600
| Rapporteur | 1 | 50000 | 1 | 50000 | 500
[5 empty] | 0 | 0
[5 empty] | 464000 | 4640
1.5 | Conduct a two -day workshop of Coalition partners to brainstorm and develop the a work plan, Theory of Change and national campaign and influencing strategy for the National Coalition
| Conference costs for 25 pax @ 4,000 pp for 1 day | 25 | 4000 | 2 | 200000 | 2000
| Accomodation and meals for 25 pax | 25 | 12000 | 3 | 900000 | 9000
| Material costs (printing, photocopying, mobilization, PPEs etc) | 1 | 30000 | 1 | 30000 | 300
| Transport reimbursements to participants | 17 | 2000 | 2 | 68000 | 680
| Coordination transport for staff | 1 | 7000 | 2 | 14000 | 140
| Facilitation honorarium | 3 | 10000 | 2 | 60000 | 600
| Rapporteur | 1 | 50000 | 1 | 50000 | 500
[5 empty] | 0 | 0
[5 empty] | 1322000 | 13220
1.5.1 | Develop Terms of Reference and recruit consultant for the Theory of Change
| Engage a consultant | 1 | 30000 | 9 | 270000 | 2700
| Sub total |  |  |  | 270000 | 2700
1.5.2 | Conduct a meeting of the national steering committee to validate the Theory of Change
| Data reimbursements | 25 | 2000 | 1 | 50000 | 500
| Mobilization | 1 | 5000 | 1 | 5000 | 50
| Subtotal |  |  |  | 55000 | 550
1.5.3. | Develop Terms of Reference for a consultant for work plan development and for communications & campaign strategy
| Engage a consultant | 1 | 30000 | 9 | 270000 | 2700
| Sub total |  |  |  | 270000 | 2700
1.5.4. | Conduct meeeting of the national steering committee to validate the work plan and campaign strategy
| Data reimbursements | 25 | 2000 | 1 | 50000 | 500
| Mobilization | 1 | 5000 | 1 | 5000 | 50
| Subtotal |  |  |  | 55000 | 550
| Project Activities Total |  |  |  | 6992000 | 69920
Contribution To Project Staff Salaries
| Program Manager Health & Governance % of staff time per month | 1 | 128000 | 6 | 768000 | 7680
| Program Officer Health & Governance % of staff time per month | 1 | 120000 | 6 | 720000 | 7200
| DED % of staff time per month | 1 | 80000 | 6 | 480000 | 4800
| Executive Director % of staff time per month | 1 | 50000 | 6 | 300000 | 3000
| M & E advisor % of staff time per month | 1 | 75000 | 6 | 450000 | 4500
| Finance & Administration Manager % of staff time per month | 1 | 90000 | 6 | 540000 | 5400
| Communications Officer % of staff time per month | 1 | 75000 | 6 | 450000 | 4500
| Sub total |  |  |  | 3708000 | 37080
General Office Administration Costs
| Utilities, Internet Costs @ 250,000 per month | 1 | 341666.67 | 6 | 2050000.02 | 20500.0002
| Sub total |  |  |  | 2050000.02 | 20500.0002
| Total budget |  |  |  | 12750000.02 | 127500.0002

## Budget
TRANSFORM HEALTH KENYA COALITION BUDGET ( AUGUST 2022- JULY 2024)
|  | No. | Unit Cost | Frequency | Unit of Frequency | Total (Kshs) | Year 1 | Year 2 | Total (USD)
Objective 1: Laws and policies on digital health technologies to achieve UHC commitments are developed and adopted at both national and county level by 2030
Sub - Objective 1.1: Advocate for enactment of E-Health Laws in Kenya that advances the development, adoption and use of digital health technologies (to achieve UHC commitments
1.1.1: | Develop a Human Rights Centered Legislative Guide of best practices adopted under international, regional and domestic frameworks and champion for its adoption.
| Engage a consultant | 1 | 40000 | 10 | Per day | 400000 | 400000 |  | 3883.4951
| Validation | [7 empty] | 0
| Data reimbursements for participants | 30 | 2000 | 1 | Per person | 60000 | 60000 |  | 582.5243
| Printing |  |  |  |  | 0 |  |  | 0
| Printing of best practice guide | 600 | 1000 | 1 | Per IEC | 600000 | 600000 |  | 5825.2427
0
| Sub total |  |  |  |  | 1060000 | 1060000 |  | 10291.2621
1.1.2: | Champion for the enactment of a national E-Health Act through both technical assistance to government as well as mobilisation of communities to take part in public participation forums
Technical Assistance to Government
| Full day conference package @ 3800 * 23 pax (30 participants, 2 KELIN staff, 1 facilitator) | 23 | 3800 | 3 | Per day | 262200 | 262200 |  | 2545.6311
| Honorarium for facilitator @ Ksh 10,000 | 2 | 10000 | 3 | Per meeting | 60000 | 60000 |  | 582.5243
| Rapportuer @ 10,000/= per day | 1 | 10000 | 3 | Per meeting | 30000 | 30000 |  | 291.2621
| Transport reimbursement for participants - 30 pax @ 2,000 | 20 | 2000 | 3 | Per person | 120000 | 120000 |  | 1165.0485
| Meeting material (mobilization, printing, photocopying, PPEs etc) | 1 | 20000 | 3 | Per meeting | 60000 | 60000 |  | 582.5243
| Coordination transport for staff | 1 | 10000 | 3 | Per meeting | 30000 | 30000 |  | 291.2621
| Sub total |  |  |  |  | 562200 | 562200 | 0 | 5458.2524
Community dialogue meetings
| Full day conference package @ 3,800 * 33 pax (30 participants, 2 KELIN staff, 1 facilitator) | 33 | 3800 | 3 | Per day | 376200 | 376200 |  | 3652.4272
| Honorarium for facilitator @ Ksh 10,000 | 2 | 10000 | 3 | Per meeting | 60000 | 60000 |  | 582.5243
| Rapportuer @ 10,000/= per day | 1 | 10000 | 3 | Per meeting | 30000 | 30000 |  | 291.2621
| Transport reimbursement for participants - 30 pax @ 2,000 | 30 | 2000 | 3 | Per person | 180000 | 180000 |  | 1747.5728
| Meeting material (mobilization, printing, photocopying, PPEs etc) | 1 | 20000 | 3 | Per meeting | 60000 | 60000 |  | 582.5243
| Coordination transport for staff | 1 | 10000 | 3 | Per meeting | 30000 | 30000 |  | 291.2621
| Sub total |  |  |  |  | 736200 | 736200 | 0 | 7147.5728
| Subtotal |  |  |  |  | 1298400 | 1298400 | 0 | 12605.8252
1.1.3: | Champion for the development and enactment of a county-specific e-Health law in Kisumu County through technical assistance to the county government
| Full day conference package @ 3,800 * 23 pax (30 participants, 2 KELIN staff, 1 facilitator) | 23 | 3800 | 3 | Per day | 262200 |  | 262200 | 2545.6311
| Honorarium for facilitator @ Ksh 10,000 | 2 | 10000 | 3 | Per meeting | 60000 |  | 60000 | 582.5243
| Rapportuer @ 10,000/= per day | 1 | 10000 | 3 | Per meeting | 30000 |  | 30000 | 291.2621
| Transport reimbursement for participants - 20 pax @ 2,000 | 20 | 2000 | 3 | Per person | 120000 |  | 120000 | 1165.0485
| Meeting material (mobilization, printing, photocopying, PPEs etc) | 1 | 20000 | 3 | Per meeting | 60000 |  | 60000 | 582.5243
| Return air fare for 2 staff | 2 | 20000 | 3 | Per meeting | 120000 |  | 120000 | 1165.0485
| Transfers / coordination transport for staff | 1 | 15000 | 3 | Per meeting | 45000 |  | 45000 | 436.8932
| Out of pocket allowance for staff | 2 | 2000 | 6 | Per night | 24000 |  | 24000 | 233.0097
| Accommodation for staff 2 nights @ 10,000 | 2 | 10000 | 6 | Per night | 120000 |  | 120000 | 1165.0485
| Subtotal |  |  |  |  | 841200 | 0 | 841200 | 8166.9903
1.1.4. | Identify and build capacity of women, youth, vulnerable and marginalized community champions to actively advocate for an enabling legal environment.
| Sub-granting to KP Consortium/Y-Act & White Ribbon Alliance | 1 | 1500000 | 1 | Lumpsum | 1500000 | 1500000 |  | 14563.1068
| Subtotal |  |  |  |  | 1500000 | 1500000 | 0 | 14563.1068
Sub-Objective 1.2: Advocate for people-centered digital health Standards and for standardization of digital health services and applications to achieve the goals of UHC.
1.2.1 | Conduct research to identify and analyze the existing digital health services and applications across the country and make recommendations on bests practices
| Sub-grant for research KEHIA/PHDA | 1 | 1500000 | 1 | Lumpsum | 1500000 | 1500000 |  | 14563.1068
| Subtotal |  |  |  |  | 1500000 | 1500000 | 0 | 14563.1068
1.2.2. | Conduct research to analyse the standards and guidelines (national and/or international) that informed development and operation of existing digital health services and applications in the country and make recommendations on ideal standards
| Sub-grant for research | 1 | 1500000 | 1 | Lumpsum | 1500000 | 1500000 |  | 14563.1068
| Subtotal |  |  |  |  | 1500000 | 1500000 | 0 | 14563.1068
1.2.3. | Engage state actors and private sector actors in the national and county government on the need for people centered standardization of digital health technologies
| Subgrant KEHIA/PHDA | 1 | 1500000 | 1 | Lumpsum | 1500000 |  | 1500000 | 14563.1068
| Subtotal |  |  |  |  | 1500000 | 0 | 1500000 | 14563.1068
Objective 2: Increased adoption and use of digital health technologies at the national and county government for access to equitable, affordable and quality health care;
Sub-Objective 2.1. Advocate for implementation of national government policy commitments to adopt and use digital health technologies as well as for formulation of policy commitments at county level
2.1.1. | Identify government digital health champions (national and county health informatics officers) to champion policy formulation and implementation on adoption and use of digital health technologies
| Sub-grant PS kenya/PHARM Access | 1 | 1500000 | 1 | Lumpsum | 1500000 | 1500000 |  | 14563.1068
| Subtotal |  |  |  |  | 1500000 | 1500000 | 0 | 14563.1068
2.1.2. | Support and facilitate roundtable dialogues with Ministry of Health Technical Working Groups (UHC & Health Informatics), Ministry of ICT, Media and Private Sector
| Sub-grant PS kenya/PHARM Access | 1 | 1500000 | 1 | Lumpsum | 1500000 | 750000 | 750000 | 14563.1068
| Subtotal |  |  |  |  | 1500000 | 750000 | 750000 | 14563.1068
2.1.3. | Host an annual multi-stakeholders conference during the Digital Health week as an accountability conference on the policy commitments
| Accommodation and meals for participants from out of town | 10 | 13000 | 4 | Per night | 520000 | 260000 | 260000 | 5048.5437
| Conference package for 35 pax @ 3500 pp for one day | 33 | 3500 | 2 | Per person | 231000 | 115500 | 115500 | 2242.7184
| Honorarium for facilitator @ Ksh 10,000 | 3 | 10000 | 2 | Per meeting | 60000 | 30000 | 30000 | 582.5243
| Rapportuer Fee @ 20,000/= per day | 1 | 20000 | 2 | Per meeting | 40000 | 20000 | 20000 | 388.3495
| Transport reimbursement for participants in Nairobi county | 20 | 2000 | 1 | Per person | 40000 | 20000 | 20000 | 388.3495
| Transport reimbursement for participants out of Nairobi county | 10 | 6000 | 3 | Per person | 180000 | 90000 | 90000 | 1747.5728
| Transfers and coordination | 1 | 33500 | 2 | Lumpsum | 67000 | 33500 | 33500 | 650.4854
| Design of banners/report/IEC | 1 | 20000 | 10 | Lumpsum | 200000 | 100000 | 100000 | 1941.7476
| Meeting material (mobilization, PPEs etc) | 1 | 30000 | 2 | Per meeting | 60000 | 30000 | 30000 | 582.5243
| Media engagement/livestreming costs | 1 | 200000 | 2 | Per meeting | 400000 | 200000 | 200000 | 3883.4951
| Printing of materials for launch | 700 | 800 | 2 | Per item | 1120000 | 560000 | 560000 | 10873.7864
| Sub total |  |  |  |  | 2918000 | 1459000 | 1459000 | 28330.0971
Sub -objective 2.2. : Increase public demand for adoption and use of digital health technologies
2.2.1. | Engage in media campaign to raise public awareness on fundamental role of digital health technologies in achieving UHC; and create demand for use and adoption on digital health technologies
| Sub-grant to WRA / Y-ACT / KP Consortium | 1 | 1500000 | 1 | Lumpsum | 1500000 | 750000 | 750000 | 14563.1068
| Sub total |  |  |  |  | 1500000 | 750000 | 750000 | 14563.1068
2.2.2. | Develop a community-led monitoring and accountability system and engage adolescents, youth, women and KP champions to, through use of score-cards, track commitments and assess the adoption and use of digital health systems
| Sub-grant to WRA / Y-ACT / KP Consortium | 1 | 1500000 | 1 | Lumpsum | 1500000 | 750000 | 750000 | 14563.1068
| Sub total |  |  |  |  | 1500000 | 750000 | 750000 | 14563.1068
Objective 3: Increased resources at national and county level for strengthening digital health technologies to achieve UHC commitments
Sub-Objective 3.1. Generate evidence and advocate for the inclusion of digital health technologies in the budget allocations
3.1.1. | Conduct a resource gap analysis to identify the resources required to achieve efficient use and adoption of digital health technologies.
| Sub grant Path | 1 | 1500000 | 1 | Lumpsum | 1500000 | 1500000 |  | 14563.1068
| Sub total |  |  |  |  | 1500000 | 1500000 | 0 | 14563.1068
3.1.2. | Engage national and county government officials using the evidence generated above on the inclusion of digital health technologies in budget allocations.
| Sub grant Path | 1 | 1500000 | 1 | Lumpsum | 1500000 |  | 1500000 | 14563.1068
| Sub total |  |  |  |  | 1500000 | 0 | 1500000 | 14563.1068
3.1.3. | Enhance capacity and support youth, women, vulnerable and marginalized groups champions to engage in budget making processes and advocate for prioritization of resources for digital health technologies
| Sub granting to Y-Act/WRA/KP Consortium | 1 | 1500000 | 1 | Lumpsum | 1500000 | 750000 | 750000 | 14563.1068
[6 empty] | 1500000 | 750000 | 750000 | 14563.1068
4. COALITION GOVERNANCE, GROWTH & DEVELOPMENT
4.1. | Identify and invite new members to the coalition
| Staff time | 1 | 0 | 1 |  | 0 |  |  | 0
4.2. | Conduct annual capacity building of coalition members on emerging issues with regards to digitial health technologies and UHC
| Conference costs for 35 pax @ 3,500 pp for 2 days | 35 | 3500 | 4 | Per day | 490000 | 245000 | 245000 | 4757.2816
| Accommodation and meals for 35 pax for 3 nights | 35 | 13000 | 6 | Per day | 2730000 | 1365000 | 1365000 | 26504.8544
| Daily subsistence allowance | 35 | 2000 | 6 | Per day | 420000 | 210000 | 210000 | 4077.6699
| Material costs (printing, photocopying, mobilization, PPEs etc) | 1 | 20000 | 2 | Per meeting | 40000 | 20000 | 20000 | 388.3495
| Transport reimbursements to participants | 30 | 6000 | 2 | Per person | 360000 | 180000 | 180000 | 3495.1456
| Coordination transport | 1 | 60000 | 4 | Per trip | 240000 | 120000 | 120000 | 2330.0971
| Facilitation honorarium | 3 | 10000 | 4 | Per meeting | 120000 | 60000 | 60000 | 1165.0485
| Rapporteur | 1 | 50000 | 2 | Per meeting | 100000 | 50000 | 50000 | 970.8738
[6 empty] | 4500000 | 2250000 | 2250000 | 43689.3204
4.3. | Conduct Quarterly Meetings of the Coalition to review progress in implementation of strategy and plan for upcoming interventions
| Half day conference for 25 pax | 25 | 3000 | 8 | per meeting | 600000 | 300000 | 300000 | 5825.2427
| Transport reimbursements for participants | 23 | 2000 | 8 | per person | 368000 | 184000 | 184000 | 3572.8155
| Coordination transport | 1 | 6000 | 8 | per meeting | 48000 | 24000 | 24000 | 466.0194
[6 empty] | 1016000 | 508000 | 508000 | 9864.0777
4.4 | Develop a website and social media platforms for Transform Health Kenya Coalition
| Engage consultant in site development | 1 | 40000 | 30 | Per day | 1200000 | 1200000 |  | 11650.4854
[6 empty] | 1200000 | 1200000 | 0 | 11650.4854
COALITION MANAGEMENT
Contracts with Partner, Subgrantees and Contractor
| Capacity assessment | 8 | 30000 | 1 | per institution | 240000 | 240000 |  | 2330.0971
| institutional stregthening | 1 | 400000 | 1 | Lumpsum | 400000 | 400000 |  | 3883.4951
| Sub total |  |  |  |  | 640000 | 640000 | 0 | 6213.5922
Direct Project Management
| Program Manager Health & Governance 20% of staff time per month | 1 | 96000 | 24 | Per month | 2304000 | 1152000 | 1152000 | 22368.932
| Program Officer Health & Governance 60% of staff time per month | 1 | 90000 | 24 | Per month | 2160000 | 1080000 | 1080000 | 20970.8738
| DED 10% of staff time per month | 1 | 55000 | 24 | Per month | 1320000 | 660000 | 660000 | 12815.534
| Executive Director 5% of staff time per month | 1 | 35000 | 24 | Per month | 840000 | 420000 | 420000 | 8155.3398
| Advocacy and Campaign Officer 100% | 1 | 200000 | 24 | Per month | 4800000 | 2400000 | 2400000 | 46601.9417
| Sub total |  |  |  |  | 11424000 | 5712000 | 5712000 | 110912.6214
| Project Activities Total |  |  |  |  | 41397600 | 24627400 | 16770200 | 401918.4466
Indirect Project Management Costs
| M & E advisor 20% of staff time per month | 1 | 76000 | 24 | Per month | 1824000 | 912000 | 912000 | 17708.7379
| Finance & Administration Manager 20% of staff time per month | 1 | 75000 | 24 | Per month | 1800000 | 900000 | 900000 | 17475.7282
| Communications Officer 20% of staff time per month | 1 | 70000 | 24 | Per month | 1680000 | 840000 | 840000 | 16310.6796
| Sub total |  |  |  |  | 5304000 | 2652000 | 2652000 | 51495.1456
General Office Administration Costs
| Utilities, Internet Costs @ 150,000 per month | 1 | 200000 | 24 | Per month | 4800000 | 2400000 | 2400000 | 46601.9417
| Sub total |  |  |  |  | 4800000 | 2400000 | 2400000 | 46601.9417
| Grant Total |  |  |  |  | 51501600 | 29679400 | 21822200 | 500015.534 | 0
[7 empty] | 288149.5146 | 211866.0194

## Workplan 2022 to 2024
Final Kenya NCP Workplan ME and Budget 2 Years (2022- 2024)
TRANSFORM HEALTH COALITION (THC) KENYA
OBJECTIVES
1. Laws and policies on digital health technologies to achieve UHC commitments are developed and adopted at both national and county level by 2030
2. Increased adoption and use of digital health technologies at the national and county government for access to equitable, affordable and quality health carecare;
3. Increased resources at national and county level for strengthening digital health technologies to achieve UHC commitments
ACTIVITY | Budget (USD) | who is responsible for delivery (suggested organisations to be invited to express interest and sub granted to implement the intervention) | OUTPUT | INDICATOR | OUTCOMES | INDICATOR TARGET | COLLABORATING PARTNERS | YOUTH, WOMEN, MARGINALISED COMMUNITIES | NEXT STEPS | STATUS | Timeline | [29 empty] | TRANSFORM HEALTH COMMENTS
[11 empty] | 2021 |  |  |  |  | 2022 | [12 empty] | 2023
[11 empty] | A | S | O | N | D | J | F | M | M | A | M | J | J | A | S | O | N | D | J | F | M | A | M | J | J | A | S | O | N | D
Objective 1:Laws and policies on digital health technologies to achieve UHC commitments are developed and adopted at both national and county level by 2030 |  | THC Kenya | (i) E-Health Laws developed and enacted at county and national level; (ii) People-Centred digital health standards adopted | i) Number of Laws / policies developed and adopted; (ii) Number of Standards developed and adopted; (iii) Laws, policies and standard adopted that align with Transform Health Kenya's messaging | Enabling legal and policy environment at both national and county level | 1 national law;1 county law; 1 national standard | Ministry of Health, Kisumu County Government, Ministry of ICT | Y-Act, WRA, KP Consortium
Sub - objective 1.1: Advocate for enactment of E-Health Laws in Kenya that advances the development, adoption and use of digital health technologies (to achieve UHC commitments. |  | THC Kenya | (i) E-Health Laws developed and enacted at county and national level; | (i) One E-Health law enacted at National Level; (ii) Number of E-Health laws enacted at county level | Enabling legal and policy environment at both national and county level | 1 national law;1 county law; | Ministry of Health, Kisumu County Government, Ministry of ICT
1.1.1: Develop a Human Rights Centered Legislative Guide of best practices adopted under international, regional and domestic legal frameworks; for use in advocacy |  | KELIN | (i) Legislative Guide Developed; (ii) Advocacy report | (i) No. of legislative guides published; (ii) No. of legislative guides disseminated to policy makers; (iii) No. of advocacy initiatives that are making use of the legislative guide | Evidence generated for legal and policy change | 1 legislative guide; 500 copies of legislative guides disseminated | Coalition Partners, Ministry of Health, Kisumu County Government, Ministry of ICT
1.1.2: Champion for the enactment of a national E-Health Act through both technical assistance to government as well as mobilisation of communities to take part in public participation forums |  | KELIN | (i) Report of Technical Assistance to government; (ii) Report of support to communities to participate in public participation forums | (i) No. of technical meetings with government on the E-Health Bill; (ii) No. of consultative forums with communities; (iii)No. of community representatives actively taking part in public participation forums | Enabling legal environment at the national level | 3 Technical Meetings on E-Health Bill; 3 Community Dialogues on E-Health Bill; 10 Community representatives taking part in public participation on E-Health Bill | Coalition Partners, Ministry of Health, Ministry of ICT, youth, women, and marginalised communities
1.1.3. Champion for the development and enactment of a county-specific e-Health law in Kisumu County through technical assistance to the county government |  | KELIN | (i) Report of Technical Assistance to Kisumu County Government; | (i) No. of technical meetings with Kisumu County Government on a E-Healthlaw; | Enabling legal environment at the county level | 3 Technical meetings on a county e-Health law | Coalition Partners, Kisumu County Government
1.1.4. Identify and build capacity of women, youth, vulnerable and marginalized community champions to actively advocate for an enabling legal environment. |  | Y-ACT / WRA / KP consortium | (i) Increased capacity of youth, women and KP champions to participate in law making processes | (i) No. of youth, women, and KP champions trained; (ii) No. of trained youth, women and KP champions actively participating in law making processes | Enhanced capacity of youth, women and Key Populations to advocate for an enabling legal environment at both national and county level | 20 youth; 20 women and 20 KP champions trained and engaged | Coalition Partners
Sub-Objective 1.2: Advocate for people-centered digital health Standards and for standardization of digital health services and applications to achieve the goals of UHC. |  | THC Kenya | (i) People-centred digital health standards adopted | National Digital Health Standards Adopted | Enabling policy framework at national level | 1 national policy | Coalition partners
1.2.1 Conduct research to identify and analyze the existing digital health services and applications across the country and make recommendations on bests practices |  | KEHIA /PHDA | (i) Research Report identifying the exsting digital health services and applications | (i) No. of research reports published; (ii) No. of research reports disseminated; (iii) No. of advocacy initiatives that are making use of the research report | Evidence generated for legal and policy change | 1 Research Report; 500 copies disseminated | Coalition partners; National & County Government State actors, private sector actors
1.2.2. Conduct research to analyse the standards and guidelines (national and/or international) that informed development and operation of existing digital health services and applications in the country and make recommendations on ideal standards |  | KEHIA/PHDA | (i) Research Report on standards and guidelines | (i) No. of research reports published; (ii) No. of research reports disseminated; (iii) No. of advocacy initiatives that are making use of the research report | Evidence generated for legal and policy change | 1 Research Report ; 500 copies disseminated | Coalition partners, National & County Government State actors, private sector actors
1.2.3. Engage state actors and private sector actors in the national and county government on the need for people centered standardization of digital health technologies. |  | KEHIA/PHDA | (i) Enagement meeting reports utilising above research | (i) No. of meetings held; (ii) No of state actors and private sector actors engaged | Enabling policy framework at national level | 30 state actors and 30 private sector actors engaged | Coalition partners, National & County Government State actors, private sector actors
Objective 2: Increased adoption and use of digital health technologies at the national and county government for access to equitable, affordable and quality health care; |  | THC Kenya | Digital health technologies adopted and used by both national and county governments | (i) No. of policy commitments to utilise digital health technologies implemented; (ii) No. of county governments making policy commitments to utilise digital technologies; (iv) No. of county governments implementing digital health policy commitments | Increased access to equitable, affordable and quality health care as a result of increase in use of digital health technologies by national and county governments | 1 national; 10 county governments | Ministry of Health, Ministry of ICT, 4 County Governments (UHC Pillot counties - Kisumu, Isiolo, Nyeri, Machakos)
Sub-Objective 2.1. Advocate for implementation of national government policy commitments to adopt and use digital health technologies as well as for formulation of policy commitments at county level |  | THC Kenya | Digital health technologies adopted and used by both national and county governments | (i) No. of policy commitments to utilise digital health technologies implemented; (ii) No. of county governments making policy commitments to utilise digital technologies; (iv) No. of county governments implementing digital health policy commitments | Increased access to equitable, affordable and quality health care as a result of increase in use of digital health technologies by national and county governments | 1 national; 4 county governments policy commitments formulated / implemented | Ministry of Health, Ministry of ICT, 4 County Governments (UHC Pillot counties - Kisumu, Isiolo, Nyeri, Machakos)
2.1.1. Identify government digital health champions (national and county health informatics officers) to champion policy formulation and implementation on adoption and use of digital health technologies |  | PS Kenya/ Pharm Access | (i) Mapping and engagement meeting reports | (i) No. of government digital health champions identified; (ii) No. of engagements with the champions | Increased access to equitable, affordable and quality health care as a result of increase in use of digital health technologies by national and county governments | 20 champions from 4 counties; 1 advocacy and action planning forum with the champions; 3 follow up review meetings | Ministry of Health, Ministry of ICT, 4 County Governments (UHC Pillot counties - Kisumu, Isiolo, Nyeri, Machakos)
2.1.2. Support and facilitate roundtable dialogues with Ministry of Health Technical Working Groups (UHC & Health Informatics), Ministry of ICT, Media and Private Sector |  | PS Kenya / Pharm Access | (i) Roundtable dialogue reports | (i) No. of roundtable dialogues; (ii) No. of commitments formulated / implemented as a result of the dialogues | Increased access to equitable, affordable and quality health care as a result of increase in use of digital health technologies by national and county governments | 3 National Round Table; 3 forums per county in 4 counties; 15 State actors engaged at national level; 15 State actors engaged in each of the 4 counties | Ministry of Health, Ministry of ICT, 4 County Governments (UHC Pillot counties - Kisumu, Isiolo, Nyeri, Machakos)
2.1.3. Host an annual multi-stakeholders conference during the Digital Health week as an accountability conference on the policy commitments |  | PS Kenya/ Pharm Access | (i) Conference report | (i) No. of conferences held; (ii) No. of commitments formulated / implemented as a result of the conference | Increased access to equitable, affordable and quality health care as a result of increase in use of digital health technologies by national and county governments | 2 national conferences; 50 people participating | Ministry of Health, Ministry of ICT, 4 County Governments (UHC Pillot counties - Kisumu, Isiolo, Nyeri, Machakos)
Sub-objective 2.2: Increase public demand for adoption and use of digital health technologies |  | THC Kenya | Increased public demand for adoption and use of digital health from youth, women, and key population groups | No. of public demands (Petitions, Letters, etc) from youth, women KP groups supporting the adoption of use of digital health technologies | Increased access to equitable, affordable and quality health care as a result of increase in use of digital health technologies by national and county governments | 1 national; 4 county governments policy commitments formulated / implemented | Coalition Partners, media, Ministry of Health, UHC pilot counties
2.2.1. Engage in media campaign to raise public awareness on fundamental role of digital health technologies in achieving UHC; and create demand for use and adoption on digital health technologies ; |  | Y-ACT / WRA / KP Consortium | (i) Media Campaign Strategy; (ii) Media Campaign Report | (i) No. of media activities; | Increased access to equitable, affordable and quality health care as a result of increase in use of digital health technologies by national and county governments | 30 media activities | Coalition Partners, Media,
2.2.2. Develop a community-led monitoring and accountability system and engage adolescents, youth, women and KP champions to, through use of score-cards, track commitments and assess the adoption and use of digital health systems |  | WRA / Y-ACT / KP Consortium | (i) Scorecard developed; (ii) Score card reports from youth, women and KP champions | (i) No. of scorecard developed; (ii) No. of community champions utilising the scorecards | Increased access to equitable, affordable and quality health care as a result of increase in use of digital health technologies by national and county governments | 30 youth, women and KP champions utilising the scorecard | Coalition Partners, Ministry of Health, County Governments
3. Increased resources at national and county level for strengthening digital health technologies to achieve UHC commitments |  | THC Kenya | Increased resources for digital health at national and county level | Amount of resouces allocated to digital health at national and county level | Increased resources at national and county level for strengthening digital health technologies to achieve UHC commitments | Increased national resources; Increased resources in four UHC pilot counties | Coalition Partners, Ministry of Health, County Governments
Sub-Objective 3.1. Generate evidence and advocate for the inclusion of digital health technologies in the budget allocations |  | THC Kenya | Evidence generated for advocacy to increase resources for digital health | Amount of resouces allocated to digital health at national and county level | Increased resources at national and county levels for strengthening digital health technologies to achieve UHC commitments | Increased national resources; Increased resources in four UHC pilot counties | Coalition Partners, Ministry of Health, County Governments
3.1.1. Conduct a resource gap analysis to identify the resources required to achieve efficient use and adoption of digital health technologies. |  | PATH Kenya | (i) Resource Gap Analysis Report | (i) No. of research reports published; (ii) No. of research reports disseminated; (iii) No. of advocacy initiatives that are making use of the research report | Increased resources at national and county levels for strengthening digital health technologies to achieve UHC commitments | 1 Research Report ; 500 copies disseminated | Coalition Partners, Ministry of Health, County Governments
3.1.2. Engage national and county government officials using the evidence generated above on the inclusion of digital health technologies in budget allocations. |  | PATH Kenya | (i) Engagement meeting reports | No. of engagements with national and county government officials | Increased resources at national and county levels for strengthening digital health technologies to achieve UHC commitments | 2 national engagements; 2 county engagements in each of the 4 pilot counties | Coalition Partners, Ministry of Health, County Governments
3.1.3:Enhance capacity and support youth, women, vulnerable and marginalized groups champions to engage in budget making processes and advocate for prioritization of resources for digital health technologies |  | Y-ACT / WRA / KP consortium | (i) Capacity building report; (ii) Report of support provided | No. of youth, women, KP groups actively engaging in budget making processes | Increased resources at national and county levels for strengthening digital health technologies to achieve UHC commitments | 30 youth, women, KP champions actively engaging in budget making processes | Coalition Partners, Ministry of Health, County Governments
4. COALITION GOVERNANCE, GROWTH & DEVELOPMENT
4.1. Identify and invite new members to the coalition |  | KELIN | Commitment letters signed | No. of new members | Growth of coalition | 10 per year | Coalition partners | bar: 2022 M to 2023 D
4.2. Conduct annual capacity building of coalition members on emerging issues with regards to digitial health technologies and UHC |  | KELIN | Training meeting report | No. of coalition members trained; Increase in knowledge | Increase in knowledge of coalition partners on emerging issues | 2 trainings conducted; 20 members trained | Coalition partners | bar: 2022 A to 2022 O
4.3 Conduct Quarterly Meetings of the Coalition to review progress in implementation of strategy and plan for upcoming interventions |  | KELIN | Reviewmeeting reports | No. of coalition members taking part in the meetings; Progress report of activities | Coordinated implementation of activities | 4 review meetings per year; 20 members taking part in each meeting | Coalition partners | bar: 2022 M; 2022 S; 2023 J; 2023 M; 2023 S
4.4. Develop a website and social media platforms for Transform Health Kenya Coalition |  | KELIN | Website and social media platforms | Website and social media engagement reports | Wider reach of Transform Health advocacy messages | messaging reaching 1 million people | Coalition partners | bar: 2022 M to 2022 O
4.5. Joint Fundraising |  | KELIN, TH Kenya Resource Mobilisation Committee & Transform Health | - At least 5 funding partners identified and approached; - At least 3 funding proposals developed and submitted with the Enabling Function to fund coalition activities between 2023 and 2024. | No of funding partners identified No of funding proposals submitted Amount of resources fundraised | Coalition growth, sustainability and development | - TH Kenya raises $368,469 to cover 50% of coalition expenses in 2023 and 2024. | Coalition Partners Fundraising committee | bar: 2022 M to 2022 O

## Budget splits
Direct | 401918.4466
Indirect | 98097.0874
24.41%
Grants | 160194.1748
32.04%
PharmAccess and PATH | 58252.4272
36.36%

## M&E
MONITORING & EVALUATION FRAMEWORK 6 months
STRATEGY & ACTIVITY | OUTPUT | OUTCOME | IMPACT
|  |  |  | Impact Indicators | Indicator | NC - Kenya
|  |  |  | Outcome Indicators | Indicator
|  |  |  | 2.1 | Number of national youth and women-led organisations, medical professional associations and civil society organisations in at least six priority countries engaged by Transform Health that are actively campaigning in support of coalition priorities. | 15
|  |  |  | 2.2 | Number of national-level decision-makers in at least six priority countries engaged by Transform Health who have publicly recognised the fundamental role of digital technology and data to achieve UHC. | 2
|  |  |  | 2.4 | Number of states and non-state digital health actors that have demonstrated support for creating a global health data governance framework. | 10 | 1
|  |  |  | 2.5 | Number of countries with effective national or regional governance mechanisms for health data.
|  |  |  | 2.6 | Number of countries that have created/strengthened effective national policies/regulations on health data. | 1
|  |  |  | 2.7 | Number of countries with digital health strategies that prioritise PHC and core principles. | 1
|  |  |  | Output indicators | Indicator
|  |  |  | 3.1 | Number of national campaign platforms established and in operation. | 1
|  |  |  | 3.2 | Pieces of media generated about/by Transform Health. | 5
|  |  |  | 3.3 | Number of individuals participating in global, regional and national campaign activities. | 50
|  |  |  | 3.4 | Number of national and regional policymakers engaged by Transform Health. | 10
|  |  |  | 3.5 | Number of other digital health actors engaged by Transform Health. | 40
|  |  |  | 3.7 | Number of non-government partners (IOs, academia, civil society, foundations, for profit) endorsing global health data governance principles. | 20
|  |  |  | 3.9 | Number of global, regional and national partners that have integrated the call for stronger health data governance into their work. | 5
|  |  |  | 3.10 | Number of high-level champions advocating for stronger global governance of health data. | 2
|  |  |  | 3.12 | Number of national decision-makers and partners engaged by Transform Health on health data governance. | 5
|  |  |  | 3.16 | Number of Transform Health engagements in national policy and budgetting processes. | 1
|  |  |  | 3.17 | Number of national reports produced by Transform Health or partners on the status of national digital health strategies and budgets. | 1
|  |  |  | 3.20 | Number of campaign activities driven by youth, women and marginalised communities. | 5
|  |  |  | 3.21 | Number of youth and women-led partners engaged in national campaign activities. | 10
|  |  |  | 3.22 | Number of skill-sharing and capacity-building activities held to meet needs identified by partners. | 1
|  |  |  | 3.23 | Total number of partners participating in the coalition (by type of organisation and geographic region). | 20

## TAB 3 M&E (hidden)
MONITORING & EVALUATION FRAMEWORK 6 months
STRATEGY & ACTIVITY | OUTPUT | OUTCOME | IMPACT